## Sheet1
Epic | User Story | Details/Comment
Authorization and Authentication | System: Authenticate via integration with Workday | Users will download the mobile app from App Store or Market Play. Will there be a process of account registration? Or, will an account be pre-created when an employee is hired, and deactivated when an employee is terminated, and re-activated when they are hired again? When a former employee is hired again, the business requirement is for the user to be able to use the app again, but not necessarily see historical journeys.
Authorization and Authentication | Log in with a pincode, touch ID or face ID | Additional security layer, for cases like a mobile phone was lost, stolen, and other. Shall users be able to remain logged in? Or, shall they log in each time?
Authorization and Authentication | System: Automatically log a user out if they have changed their password for the SoftServe business systems.
Authorization and Authentication | Exceptions handling | User account locked due to password expiration. Other exceptions TBD.
Admin | Assign Admin user role to user | All users will have regular user permissions (driver and passenger capabilities). A few users will have Admin user role assigned, in addition to that.
User Account | View own account | The following data will be auto-populated from Workday and cannot be edited: names, photo, job title, office location. Home address is not relevant and will not be displayed or editable.
User Account | View another employee's account | All data will be read-only.
User Account | System: Sync data from Workday | For example, if a surname or office location is changed.
User Account | Add comment | User will be able to add comment about themselves. This data will also live in the application and not be sync'd back to Workday.
User Account | Add preferences (no animals, no smoking, music) | the focus is on what an employee does not want.
User Account | System: show employee's preferences on every journey | So that users do not have to open an employee's account each time.
Car Information | Add/update a car | Car number will not be there. Color shall be optional. Manufacturer and car model shall be required fields. No photos of cars will be uploaded. Assumption: this one and only car will be used on all journeys (Need to validate this assumption. Shall user to able to have a few cars added in the app?)
Journey Statuses | Display journey status | The following statuses can be used (preliminary): New, Done, and Canceled.
Journey Statuses | System: Set "Done" status to all "New" journeys at 12 am if the journey date passes | This automated process is a preliminary suggestion. Another solution can be suggested and implemented. The business need is NOT to impose an extra action of completing a journey in the app onto the drivers.
Create Journeys as Driver | Create/update a journey by own car | Specify date and time, and number of available seats.
Create Journeys as Driver | Delete a journey | No passengers booked seats yet. So, the journey can be deleted altogether. Maybe, it was created as a test or by mistake.
Create Journeys as Driver | Cancel a journey | Passengers booked seats. System will need to notify them of the cancellation.
Create Journeys as Driver | Specify address of departure, address of destination, and intermediate stops/points of the route | Intermediate stops/points of the route shall be optional for a driver to specify.
Search for Journeys as Passenger | View all future journeys (not fully booked) | Display on top of the app the number of all journeys that already happened today - nice to have feature (motivation to use the app.
Search for Journeys as Passenger | System: Do not display journeys with a date and time prior to the current date and time | Past journeys shall not display and clutter the screen.
Search for Journeys as Passenger | System: Do not allow re-using journeys | Do not allow editing them if the date is in the past. Time is fine to edit (maybe, there was just a delay).
Search for Journeys as Passenger | Mark a journey as recurrent | If a driver goes the same route every day.
Search for Journeys as Passenger | System: Suggest cloning a journey for a future date given there is "Recurrent" flag | Maybe, auto-create when the date passes. System popup "Would you like to drive tomorrow?" and a driver can confirm. The business requirement: a driver does not have to create similar journeys from scratch, on the one hand, and there shall be no invalid journeys (auto-created), on the other hand. Maybe, system can track something like "I see you drive 3 times to the same place. Would you like to make it regular?" | manual feedback - якщо люди здружились. Користуєтесь чи ні
Search for Journeys as Passenger | Search for a journey by departure and destination points (cities) and date
Search for Journeys as Passenger | Search for a journey by departure and destination points (SoftServe offices) and date
Search for Journeys as Passenger | Search for a journey by departure and destination points (address) and date | Addresses can be plain text. But it is better to select them using geo-location. Geo-location for "from where" and "to where"
Search for Journeys as Passenger | View a journey | The following data shall display: date, time, from where, to where, intermediate points if any, who the driver, car, who the passengers (hyperlinked names). User shall be able to navigate to the driver or a passenger's accounts (profiles), even if they haven't booked a seat on the journey yet.
Search for Journeys as Passenger | Apply for a journey by car | Book a seat on a journey
Search for Journeys as Passenger | Withdraw application | Withdraw your own booking as a passenger
Search for Journeys as Passenger | Approve application/booking | A driver shall have a capability to agree to take on a specific passenger or not
Journey Request | Create/update a journey request as a passenger
Journey Request | Create/update a journey as a driver and invite a passenger | Maybe, system can auto-suggest to a driver that there are journey requests.
Journey Request | Accept the invitation as a passenger
Future Journeys | View list of own future journeys as a Driver
Future Journeys | View list of own upcoming journeys as a Passenger
Historical Journeys | View list of own historical journeys as a Driver
Historical Journeys | View list of own historical journeys as a Passenger
Dictionaries | SoftServe offices | Integration with Workday
Taxi Cost Sharing | Create/update a journey by taxi
Taxi Cost Sharing | Apply for a journey by taxi/book a place
Taxi Cost Sharing | Cancel a journey by taxi
Notifications | Auto: Notify driver that passenger applied | The passenger booked a seat on the journey.
Notifications | Auto: Notify passenger that driver approved application | The passenger booked a seat on the journey.
Notifications | Auto: Notify passenger that driver rejected application | The passenger booked a seat on the journey.
Notifications | Auto: Notify passenger that a journey is cancelled | The passenger booked a seat on the journey.
Notifications | Auto: Notify passenger that the journey datetime is updated | The passenger booked a seat on the journey.
Notifications | Auto: Notify passenger that the journey points (departure, destination, or intermediate) are updated | The passenger booked a seat on the journey.
Notifications | Auto: Notify the passenger that a driver or taxi organizer invited them on a journey | The passenger created a journey request.
Notifications | Auto: Notify the driver or taxi organizer that the passenger accepted the invitation | The passenger created a journey request.
Notifications | Auto: Notify the driver or taxi organizer that the passenger rejected the invitation | The passenger created a journey request.
Notifications | Auto: Notify the driver that a passenger withdrew their application. | The passenger booked a seat on the journey. The driver approved the application.
Instant Messaging | Chat between driver and a single specific passenger | It should be an internal messaging tool (no integrations with Teams, etc.). Chat between driver and one passenger. Auto-available for each journey. As a driver, you can communicate with each Passenger separately. What if a driver needs to notify a whole group of passengers?
Integrations | Google map for addresses | Use cases: See the destination point on the map. See if two offices are close.
Legal | Terms of Use | Use recommendation policy
User Guide | Q&A, mini tutorial | A few pages. Interactive onboarding.
Admin | Manage text of the auto-notifications | HR Marketing shall be able to edit the texts (see "Notifications" epic). They shall not be hard-coded.
HR Marketing Messages | Send custom messages | Admin shall be able to send popup messages. All active users shall be able to see them. Active users are all those logged in, not necessarily the users who go on journeys. Users shall not see historical, irrelevant messages ("today or never" principle).
Contact/feedaback | Send feedback on the app or report an issue | Users shall be able to send general feedback on the app (a button that sends an email to a group email address TBD), feature needs and suggestions, or report issues/errors/inconveniences they experience with the app.
Data Storage/Cleanup | Data storage requirements and periodic cleanup | Shall data on historical journeys be cleaned up, say once half a year? Reports might be exported, but on the other hand, if a new report type needs to be run, the data will be outside the system already. Need to get advice on what is reasonable given some tech constraints and potential historical reports needs.
Analytics | View reports | Admin shall be able to see various analytics on the mobile phone.
| Badges | Select a badge(s) after the journey | Passengers select one or a few badges out of the pre-defined list.
| Price | System: Display suggested price (calculated for the distance using geo-location) | For journeys in own car and by taxi
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: не знайшла на мокапах Reply: ми казали, що збережемо цей функціонал для версії 2.0

## UserStories#
| Epic | User Story | #
1 | Authorization and Authentication | System: Authenticate via integration with Workday
| Authorization and Authentication | Log in with a pincode, touch ID or face ID
| Authorization and Authentication | System: Automatically log a user out if they have changed their password for the SoftServe business systems.
| Authorization and Authentication | Exceptions handling
2 | Admin | Assign Admin user role to user
3 | User Account | View own account
| User Account | View another employee's account
| User Account | System: Sync data from Workday
| User Account | Add comment
| User Account | Add preferences (no animals, no smoking, music)
| User Account | System: show employee's preferences on every journey
4 | Car Information | Add/update a car
5 | Journey Statuses | Display journey status
| Journey Statuses | System: Set "Done" status to all "New" journeys at 12 am if the journey date passes
6 | Create Journeys as Driver | Create/update a journey by own car
| Create Journeys as Driver | Delete a journey
| Create Journeys as Driver | Cancel a journey
| Create Journeys as Driver | Specify address of departure, address of destination, and intermediate stops/points of the route
7 | Search for Journeys as Passenger | View all future journeys (not fully booked)
| Search for Journeys as Passenger | System: Do not display journeys with a date and time prior to the current date and time
| Search for Journeys as Passenger | System: Do not allow re-using journeys
| Search for Journeys as Passenger | Mark a journey as recurrent
| Search for Journeys as Passenger | System: Suggest cloning a journey for a future date given there is "Recurrent" flag
| Search for Journeys as Passenger | Search for a journey by departure and destination points (cities) and date
| Search for Journeys as Passenger | Search for a journey by departure and destination points (SoftServe offices) and date
| Search for Journeys as Passenger | Search for a journey by departure and destination points (address) and date
| Search for Journeys as Passenger | View a journey
| Search for Journeys as Passenger | Apply for a journey by car
| Search for Journeys as Passenger | Withdraw application
| Search for Journeys as Passenger | Approve application/booking
8 | Journey Request | Create/update a journey request as a passenger
| Journey Request | Create/update a journey as a driver and invite a passenger
| Journey Request | Accept the invitation as a passenger
9 | Future Journeys | View list of own future journeys as a Driver
| Future Journeys | View list of own upcoming journeys as a Passenger
10 | Historical Journeys | View list of own historical journeys as a Driver
| Historical Journeys | View list of own historical journeys as a Passenger
11 | Dictionaries | SoftServe offices
12 | Taxi Cost Sharing | Create/update a journey by taxi
| Taxi Cost Sharing | Apply for a journey by taxi/book a place
| Taxi Cost Sharing | Cancel a journey by taxi
13 | Notifications | Auto: Notify driver that passenger applied
| Notifications | Auto: Notify passenger that driver approved application
| Notifications | Auto: Notify passenger that driver rejected application
| Notifications | Auto: Notify passenger that a journey is cancelled
| Notifications | Auto: Notify passenger that the journey datetime is updated
| Notifications | Auto: Notify passenger that the journey points (departure, destination, or intermediate) are updated
| Notifications | Auto: Notify the passenger that a driver or taxi organizer invited them on a journey
| Notifications | Auto: Notify the driver or taxi organizer that the passenger accepted the invitation
| Notifications | Auto: Notify the driver or taxi organizer that the passenger rejected the invitation
| Notifications | Auto: Notify the driver that a passenger withdrew their application.
13 | Instant Messaging | Chat between driver and a single specific passenger
14 | Integrations | Google map for addresses
15 | Legal | Terms of Use
16 | User Guide | Q&A, mini tutorial
2 | Admin | Manage text of the auto-notifications
17 | HR Marketing Messages | Send custom messages
18 | Contact/feedaback | Send feedback on the app or report an issue
19 | Data Storage/Cleanup | Data storage requirements and periodic cleanup
20 | Analytics | View reports
|  | Badges |  | Passengers select one or a few badges out of the pre-defined list.
|  | Price |  | For journeys in own car and by taxi